| - Summary information |  |  |  |
| --- | --- | --- | --- |
| School | Walbottle Village Primary School |  |  |
| Academic Year | 2020-2021 | Total Catch up fund | £14000 |
| Total number of pupils | 172 | Number of pupils eligible for PP | 61 |

| Planned Expenditure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Desired outcome | Chosen action / approach | What is the evidence and rationale for this choice? | How will you ensure it is implemented well? | When will you review implementation? | Total Cost |
| Ensure high-quality reading provision is available both at school and at home. | Provide high quality phonics resources in school for children in KS1. For those in higher year groups, these should be personalised based on individual needs. Order RWI ‘book bag books’ for children in Early Years. Order RWI non-fiction books to support children’s exposure to a range of texts. | Phonics approaches have been consistently found to be effective in supporting younger readers to master the basics of reading, with an average impact of an additional four months’ progress. Education Endowment Foundation. | Monitor progress in reading across school. Monitor high quality teaching of phonics. Offer online support for parents to show them how best to utilise resources at home. | End of Summer Term | Book Bag Books – Non-fiction - £790 Book for Early Years - £557.50 RWI online subscription - £315 (2 year subscription) |
| Build children’s resilience and emotional wellbeing following Covid-19. | Provide extracurricular activities in school to support social and emotional development. All year groups later in year to access a day trip or enjoy an extracurricular day in school in Summer Terms. Children and classes identified to be struggling with mental and emotional wellbeing to have the opportunity to work with Mental Health Practitioner. | Social and Emotional interventions have an identifiable and valuable impact on attitudes to learning and social relationships in school. They also have an average overall impact of four months' additional progress on attainment. | Evidence of successful trips linked to wellbeing and resilience. Feedback from children. | Ongoing | Staffing costs Early Years club – £60 KS1 club 3 Teaching Assistants – £60 x 3 = £180 KS2 club 2 Teaching Assistants – £60 x 2 = £120 |
| Improve outcomes for children in Year 1-6 in reading, writing and maths. | Staff to deliver high quality interventions linked to current learning and basic skills. Resources purchased to support interventions. Whiterose Maths purchased to support home-learning through videos and the recovery curriculum in school Sessions from specialist Maths Tutor to support identified children in small groups. | Research which focuses on teaching assistants who provide one to one or small group support shows a positive benefit of between three and five additional months on average. Often support is based on a clearly specified approach which teaching assistants have been trained to deliver. Education Endowment Foundation. Mastery learning appears to be particularly effective when pupils work in groups or teams and take responsibility for supporting each other’s progression. On average, mastery learning approaches are effective, leading to an additional five months’ progress. | Monitor progress. High quality interventions. | Ongoing | Staffing costs for after school intervention – TBC Resources for Intervention - £220.30 (CGP Books for Interventions and Improving quality of teaching). Whiterose Premium - £120 Spelling Shed and Maths Shed - £205 National Tutoring Cost - £877.50 Maths Resources - £500 Literacy Resources - £500 Science Resources - £220 Geography Resources - £200 |
| Children in Reception to catch up to Age Related Expectations in all areas. | An additional teacher 3 x afternoons a week in Spring 2 term to complete interventions based on phonics, counting and fine motor skills. Follow White Rose maths scheme of learning. Resources purchased to support the development of reading, writing, communication and language skills. | Evidence suggests that early years and pre-school interventions have a positive impact, delivering an average of around five additional months' progress. The approach appears to be particularly beneficial for children from low income families. Education Endowment Foundation. Evidence Suggests that Early Numeracy Approaches. On average, early numeracy approaches have a positive impact on learning equivalent to approximately six additional months’ progress for early mathematics outcomes. Education Endowment Foundation. Regular opportunities for children to engage in storytelling and group reading activities are suggested to have a positive impact of four additional months’ progress for early literacy outcomes. Education Endowment Foundation. | Ensure that interventions are targeted to specific gaps in knowledge/skills. Monitor progress of children involved in interventions. Monitor parental engagement on Tapestry. Regular planning meetings and evaluations. | Ongoing | Resources - £2000 |
| Improve communication and engagement with children and families during January 2021 lockdown. | Continue weekly calls for children who aren’t appearing to engage with home learning. | During lockdown 2021 a parental survey was sent home to establish needs, wants and areas to improve. | Monitor engagement on Tapestry/Class Dojo. Ensure staff are keeping note of children with particular needs | Parental survey will be completed during lockdown 2021. |  |